<Insert Project Name>

Template Name

Date: <Insert Date>

Document Version: V1.1

Introduction to the Risk Register	3

Section 1: General Register Information	3

Guidance for Completion	3

Fields to Include	3

Best Practice Tip	3

Section 2: Risk Definition (The "What")	4

Guidance for Completion	4

Columns to Include	4

Refining the Description	4

Section 3: Qualitative Analysis (The Scoring)	4

Guidance for Completion	4

The Probability Scale (P)	5

The Impact Scale (I)	5

The Risk Score (P x I)	5

Section 4: RAG Rating (Heatmap Status)	6

Guidance for Completion	6

The Mapping Logic	6

Draft Example	6

Section 5: Risk Response Strategy (The 4 Ts)	6

Guidance for Completion	6

Strategy 1: Treat (Mitigate)	6

Strategy 2: Transfer (Deflect)	6

Strategy 3: Terminate (Avoid)	7

Strategy 4: Tolerate (Accept)	7

Section 6: Specific Mitigation Actions	7

Guidance for Completion	7

Two Types of Actions	7

Draft Example	7

Tip for Success	7

Section 7: Risk Ownership	7

Guidance for Completion	7

The Golden Rule of Ownership	8

Draft Example	8

Section 8: Residual Risk Score	8

Guidance for Completion	8

The Calculation	8

Why this matters	8

Section 9: Risk Proximity (Timing)	8

Guidance for Completion	8

Categories	8

Draft Example	9

Section 10: Current Status Update	9

Guidance for Completion	9

Writing the Update	9

Status Flags	9

Section 11: The Register Layout (Spreadsheet Structure)	9

Guidance for Completion	9

Draft Table Structure	9

Section 12: Trigger Conditions	10

Guidance for Completion	10

Why define Triggers?	10

Draft Examples	10

Section 13: Cost of Mitigation	11

Guidance for Completion	11

The Cost-Benefit Analysis	11

Draft Example column entry	11

Section 14: Integration with Schedule	11

Guidance for Completion	11

The Linkage	11

Why this matters	11

Section 15: Review and Retirement Process	11

Guidance for Completion	11

Closing a Risk	11

Archiving	12

Detailed Tips on Negotiating Risk Scores	12

The "Optimism" Battle	12

The "Sky is Falling" Battle	12

The "Score Creep"	12

Best Practices for Risk Descriptions	12

Be Specific about "Who" and "What"	12

Quantify the "Result"	12

Avoid "Solutioneering" in the Description	12

Conclusion	13

Meta Description	13

## Introduction to the Risk Register

The transition from the "Initial Risk Identification Log" (Template 16) to the High-Level Risk Register marks a significant maturity step in the project management lifecycle. While the Identification Log is a brainstorming tool used to capture every possible worry, the Risk Register is a governance tool used to manage, track, and control specific threats to the project's success.

The Risk Register is often described as the single most important document for a Project Manager. It is the central repository where the team explicitly acknowledges that things might go wrong and, more importantly, details exactly what they intend to do about it. It moves the project from a state of "unconscious incompetence" (we don't know what we don't know) to "conscious competence" (we know the risks, and we have a plan).

This template is designed to provide a comprehensive structure for your Risk Register. It goes beyond simple data entry columns. It provides a methodology for Qualitative Risk Analysis, allowing you to score risks based on Probability and Impact. This scoring system enables you to prioritize resources. You cannot mitigate every risk; you do not have the time or money. Therefore, the Risk Register helps you decide which risks require aggressive action and which can be accepted or monitored.

This document is intended to be a "Living Document." It is not created once and filed away. It must be reviewed, updated, and re-scored at regular intervals (usually weekly or bi-weekly). A stagnant Risk Register is a sign of a dying project.

## Section 1: General Register Information

### Guidance for Completion

Before diving into the specific rows of risks, you must establish the metadata for the register itself. This ensures version control and clarity regarding who owns the document.

### Fields to Include

- Project Name: The official title.

- Project Manager: The custodian of the register.

- Last Updated: The date of the most recent review.

- Next Review Date: The scheduled date for the next Risk Workshop.

- Currency: (e.g., USD, GBP) for any financial impact estimates.

### Best Practice Tip

Include a "Risk Threshold" statement at the top. For example: "Any risk with a score higher than 15 must be escalated to the Steering Committee immediately."

## Section 2: Risk Definition (The "What")

### Guidance for Completion

This section transfers the data from the Identification Log but refines it for clarity. Ambiguity is the enemy of risk management. If a risk is vague, it cannot be scored accurately.

### Columns to Include

- Risk ID: (e.g., R-001). Keep this ID constant. If a risk is closed, do not re-use its ID. This preserves the audit trail.

- Risk Category: Use the standard headings (Technical, Commercial, Operational, Political). This allows for filtering later.

- Risk Title: A short, 5-word headline (e.g., "Server Hardware Delay").

- Risk Description: The detailed "If-Then-Result" statement.

### Refining the Description

In the Initial Log, you might have written "Vendor might be late." In the Register, you must refine this: "If the vendor fails to ship the hardware by Oct 1st due to chip shortages, then the installation phase will be delayed by 3 weeks, resulting in a missed UAT window."

## Section 3: Qualitative Analysis (The Scoring)

### Guidance for Completion

This is the engine of the register. You must assign a numerical value to the risk to understand its severity. We typically use two dimensions: Probability (Likelihood) and Impact (Consequence).

### The Probability Scale (P)

Define what the numbers mean to ensure consistency across the team.

- 1 (Rare): < 10% chance. Unlikely to happen.

- 2 (Unlikely): 10% to 30% chance.

- 3 (Possible): 30% to 60% chance. It could happen.

- 4 (Likely): 60% to 90% chance. We expect this to happen.

- 5 (Almost Certain): > 90% chance. This is arguably an issue, not a risk.

### The Impact Scale (I)

Define the damage if the risk occurs.

- 1 (Negligible): Minimal impact. < 1 day delay. < $100 cost.

- 2 (Minor): Small nuisance. < 1 week delay. < $1,000 cost.

- 3 (Moderate): Noticeable pain. 1-2 week delay. Budget contingency needed.

- 4 (Major): Critical hit. > 1 month delay. Major budget variance. Sponsor intervention required.

- 5 (Catastrophic): Project failure. The objective can no longer be met.

### The Risk Score (P x I)

Multiply Probability by Impact to get the Risk Score.

- Example: Probability (4) x Impact (4) = Score (16).

- Range: The score will range from 1 (Low) to 25 (Extreme).

## Section 4: RAG Rating (Heatmap Status)

### Guidance for Completion

Executives rarely want to see the raw numbers. They want to see colors. You must map your Risk Score to a Red-Amber-Green (RAG) status. This helps in visual reporting.

### The Mapping Logic

- Green (Low Risk): Score 1 to 6.

  - Action: Monitor. No active mitigation required.

- Amber (Medium Risk): Score 8 to 12.

  - Action: Active Management. Mitigation plan required.

- Red (High Risk): Score 15 to 25.

  - Action: Mandatory Escalation. Immediate action required.

### Draft Example

- Risk: R-004

- Score: 20

- Status: RED

- Implication: This risk is the first item on the agenda for the Steering Committee.

## Section 5: Risk Response Strategy (The 4 Ts)

### Guidance for Completion

Once you know the score, you must decide what to do. You cannot simply watch a high risk happen. You must apply one of the four standard strategies. This column tells the stakeholder your intent.

### Strategy 1: Treat (Mitigate)

You will take action to reduce the Probability or the Impact. This is the most common strategy.

- Example: Installing a sprinkler system (Treating Impact of fire) or training staff (Treating Probability of error).

### Strategy 2: Transfer (Deflect)

You will move the financial impact to a third party.

- Example: Buying insurance or signing a fixed-price contract (moving the inflation risk to the vendor). Note that you cannot transfer the reputational impact, only the financial one.

### Strategy 3: Terminate (Avoid)

You will change the project plan to eliminate the risk entirely.

- Example: If using "Technology A" is too risky, we switch to "Technology B." We have terminated the risk associated with A.

### Strategy 4: Tolerate (Accept)

You will do nothing. This is a valid strategy for low risks (Green) or risks where the cost of mitigation is higher than the cost of the impact.

- Example: The risk of a meteor strike is high impact but low probability. Mitigation is too expensive. We accept it.

## Section 6: Specific Mitigation Actions

### Guidance for Completion

The "Response Strategy" (Section 5) is just a label. This section (Section 6) details the actual work. You must be specific. "Monitor the situation" is rarely a valid action plan for a Red risk.

### Two Types of Actions

- Preventative Action: Steps taken now to stop the risk from happening. (Reduces Probability).

- Contingent Action: Steps planned for later if the risk does happen. (Reduces Impact).

### Draft Example

Risk: Vendor Delay.

- Strategy: Treat.

- Preventative Action: "Hold weekly progress reviews with the Vendor PM to identify slippage early."

- Contingent Action: "Identify an alternative supplier who can ship within 48 hours if the primary vendor fails."

### Tip for Success

Assign a deadline to these actions. "Weekly review" is good; "Review by Friday" is better.

## Section 7: Risk Ownership

### Guidance for Completion

Every risk must have a name attached to it. The "Risk Owner" is the person accountable for monitoring the risk and ensuring the mitigation actions are carried out.

### The Golden Rule of Ownership

The Risk Owner should be the person best placed to manage the risk, not necessarily the Project Manager.

- Technical Risk Owner: Lead Architect.

- Legal Risk Owner: General Counsel.

- Budget Risk Owner: Finance Director.

### Draft Example

- Risk: Regulatory Change.

- Owner: Sarah Jenkins (Compliance Officer).

- Role: Sarah does not have to do all the work, but she must report on the risk status to the Project Manager.

## Section 8: Residual Risk Score

### Guidance for Completion

This is an advanced but critical concept. The Inherent Score is the score before you take action. The Residual Score is the score after you have successfully applied your mitigation.

This shows the value of your risk management. If the Inherent Score is 20 (Red) and the Residual Score is still 20, your mitigation plan is useless. You want to show that your plan brings the risk down to an acceptable level (Green or Amber).

### The Calculation

- Inherent: Prob (5) x Impact (4) = 20 (Red).

- Mitigation: We install a backup generator.

- Residual: Prob (2) x Impact (2) = 4 (Green).

### Why this matters

Stakeholders need to know: "Are we safe now, or will we be safe later?" The Residual score represents the target state.

## Section 9: Risk Proximity (Timing)

### Guidance for Completion

Not all risks are immediate. A risk might be "High Severity" but not relevant for six months. Proximity helps you prioritize your attention.

### Categories

- Immediate: Could happen within 30 days. (Focus here).

- Near Term: Within 1-3 months.

- Far Term: > 3 months.

- Strategic: Could happen at any time (e.g., Reputation Event).

### Draft Example

- Risk: User Acceptance Testing Failure.

- Proximity: Far Term. (UAT is scheduled for December; it is currently January).

- Action: We can "Monitor" this for now and focus on the "Immediate" risks regarding Design Approval.

## Section 10: Current Status Update

### Guidance for Completion

The Risk Register is a report. You need a column to tell the reader what happened this week. This is the "Journal" section of the row.

### Writing the Update

Keep it brief and dated.

- Example: "[Oct 12]: Mitigation plan approved. Vendor contacted. Backup unit ordered."

- Example: "[Oct 19]: Backup unit arrived. Risk Probability reduced to 2. Moving to Green status."

### Status Flags

- Open: Active risk.

- Closed: Risk did not happen, or the window has passed.

- Realized: The risk happened. It is no longer a risk; it is now an Issue. (Move to Issue Log).

## Section 11: The Register Layout (Spreadsheet Structure)

### Guidance for Completion

Below is a text-based representation of the columns you should create in Excel, SharePoint, or your PPM tool.

### Draft Table Structure

| ID | Category | Risk Description | Prob (1-5) | Imp (1-5) | Score | Strategy | Mitigation Plan | Owner | Residual Score | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R-01 | Tech | If the API is incompatible... | 4 | 4 | 16 (Red) | Treat | Build a middleware layer. | Lead Dev | 4 (Green) | Open |
| R-02 | Comm | If steel prices rise... | 3 | 3 | 9 (Amb) | Transfer | Sign fixed-price contract. | PM | 3 (Green) | Open |
| R-03 | People | If Key Expert leaves... | 2 | 5 | 10 (Amb) | Tolerate | No budget for backup. | HR Lead | 10 (Amb) | Open |

## Section 12: Trigger Conditions

### Guidance for Completion

How do you know when a risk is about to happen? You identify a Trigger. This is the warning sign or the "Early Warning Indicator."

### Why define Triggers?

Triggers allow you to act fast. Instead of waiting for the disaster, you wait for the sign of the disaster.

### Draft Examples

- Risk: Budget Overrun.

  - Trigger: CPI (Cost Performance Index) drops below 0.9 for two consecutive weeks.

- Risk: Rain Delay.

  - Trigger: The 3-day weather forecast predicts >80% chance of precipitation.

- Risk: Vendor Insolvency.

  - Trigger: Vendor requests early payment or lays off staff.

## Section 13: Cost of Mitigation

### Guidance for Completion

Mitigation is not free. Treating a risk costs money. You should track this cost to ensure the cure isn't more expensive than the disease.

### The Cost-Benefit Analysis

- Risk Impact: $50,000.

- Mitigation Cost: $10,000.

- Decision: Good investment. Proceed.

- Risk Impact: $5,000.

- Mitigation Cost: $10,000.

- Decision: Bad investment. Switch strategy to "Tolerate."

### Draft Example column entry

"Est. Mitigation Cost: $5,000 (Cost of backup server rental)."

## Section 14: Integration with Schedule

### Guidance for Completion

Risks do not exist in a vacuum; they impact the timeline. Advanced risk registers link the risk to a specific "Activity ID" in the Gantt chart.

### The Linkage

- Risk ID: R-001.

- Linked Task: Task 4.2 (Server Installation).

- Impact: If R-001 occurs, Task 4.2 will extend by 5 days.

### Why this matters

This allows you to run a "Monte Carlo Analysis" later, where you simulate the schedule thousands of times to see the probable finish date based on these risks.

## Section 15: Review and Retirement Process

### Guidance for Completion

You must define when a risk is closed. A common mistake is leaving old risks on the register forever. This creates "Noise."

### Closing a Risk

A risk is closed when:

- The threat has passed: (e.g., The "Rain Risk" is closed because the roof is now on the building).

- The risk happened: (e.g., It rained). Move it to the Issue Log.

- The strategy changed: We canceled that part of the project.

### Archiving

Do not delete rows. Filter them to "Hidden" or move them to an "Archive" tab. You need the history for "Lessons Learned."

## Detailed Tips on Negotiating Risk Scores

### The "Optimism" Battle

Stakeholders will often argue for lower scores. "Oh, that won't happen, put it as a Probability 1."

- Your Rebuttal: "I appreciate the optimism; however, industry data suggests this happens in 30% of projects. Let's mark it as a 2 or 3 to be safe. We can lower it next week if we see progress."

### The "Sky is Falling" Battle

Some stakeholders want everything to be Red to get attention.

- Your Rebuttal: "If everything is Red, nothing is Red. We need to prioritize. Is this really a catastrophic impact? Would it stop the project? Or is it just a 'Minor' annoyance?"

### The "Score Creep"

Watch out for risks that stay Amber for months. If a risk is Amber for 3 months, it is effectively being "Tolerated." Challenge the owner: "Are you actually doing the mitigation, or should we just accept this risk?"

## Best Practices for Risk Descriptions

### Be Specific about "Who" and "What"

- Vague: "Staffing issues."

- Specific: "If the Data Analyst resigns before the migration is complete..."

### Quantify the "Result"

- Vague: "...then the project will be delayed."

- Specific: "...then the project will be delayed by a minimum of 2 weeks, incurring run-rate costs of $15,000."

### Avoid "Solutioneering" in the Description

Don't write the solution in the risk.

- Bad: "Risk is that we need to buy a backup server." (That is an action).

- Good: "Risk is that the primary server fails." (The action is to buy a backup).

## Conclusion

The High-Level Risk Register is the shield that protects the project from chaos. It provides a structured, rational way to deal with the irrational and unpredictable nature of the future. By maintaining this register with discipline, you demonstrate control to your stakeholders.

When a stakeholder asks, "What happens if X happens?", you should be able to open this register and say, "We have identified that as Risk R-012. It is currently scored as Amber. We have a mitigation plan in place involving X and Y, and Jane is owning it." This level of competence builds immense trust.

Remember that the goal of risk management is not to eliminate all risk (which is impossible) but to ensure that the risks are known, understood, and managed within the organization's risk appetite. Use this template to facilitate the difficult conversations about what might go wrong, so that you are prepared when it does go wrong.

Finally, keep the feedback loop open. When a risk is successfully mitigated, celebrate it. "We avoided Risk R-004 thanks to Jane's quick action." This encourages the team to engage with the process rather than seeing it as a bureaucratic burden.

### Meta Description

A template for the High-Level Risk Register. Includes detailed guidance on qualitative analysis (scoring), the 4 Ts of response strategy, residual risk, and mitigation planning.